## Bug Report
Category | Label | Value
Bug ID | ID Number | #01
| Title | alignement of navigation bars within content boxes
| Reporter | Damian knight
| Submit date | 2024-11-22
Bug overview | Summary | due to broken css elements the navbar will not display corrctly at the top of the content box
Environment | Platform | vs code
| Operating System | windows 11
| Browser | Chrome
Bug details | Steps to reproduce | Load the admin page
| Expected result | navbar at the top of the admin results box
| Actual result | navbar is being display at the top of page and stretched instead of wanted size
Bug tracking | Severity | medium
| Assigned to | Damian Knight
| Priority | High
Notes | Notes | working on moving into the correct area and sorting out the sizing
Category | Label | Value
Bug ID | ID Number | #02
| Title | tailwind wont respond
| Reporter | Damian Knight
| Submit date | 2024-12-02
Bug overview | Summary | when using tailwind classes they will not show up within the website as they should still un styled
Environment | Platform | vs code
| Operating System | windows 11
| Browser | Google Chrome
Bug details | Steps to reproduce | code tailwind classes in the classes of an element of the page,go to the website and see there has been no changes
| Expected result | elements should be styled by tailwind classes
| Actual result | no changes happened on the website
Bug tracking | Severity | Major
| Assigned to | Damian Knight
| Priority | High
Notes | Notes | need to look into the config.js file for tailwind and fix the importing
Category | Label | Value
Bug ID | ID Number | #03
| Title | library displaying dublacate library in admin box display
| Reporter | damian knight
| Submit date | 2024-12-06
Bug overview | Summary | within the admin display for librarys there is a duplicate entry of hallam library
Environment | Platform | vs code
| Operating System | windows 11
| Browser | Google Chrome
Bug details | Steps to reproduce | open the admin page,look at the library display area
| Expected result | should only contain one entry of each library
| Actual result | The cart contains only 1 item.
Bug tracking | Severity | medium
| Assigned to | John Webb
| Priority | Medium
Notes | Notes | check the admin content
Category | Label | Value
Bug ID | ID Number | #04
| Title | merge conflics with main
| Reporter | damian knight
| Submit date | 2024-12-03
Bug overview | Summary | we cant push the main changes in the front end branch to the main
Environment | Platform | vs code
| Operating System | windows 11
| Browser | Google Chrome
Bug details | Steps to reproduce | try to merge front end branch with the main branch
| Expected result | should merge
| Actual result | doesn’t merge
Bug tracking | Severity | Major
| Assigned to | damian knight
| Priority | High
Notes | Notes | needs fixing as soon as possible
Category | Label | Value
Bug ID | ID Number | #05
| Title | member is unable to get to home page from login
| Reporter | damian knight
| Submit date | 2024-12-12
Bug overview | Summary | when clicking the login button there is no response due to back end bugs not sending any data
Environment | Platform | vs code
| Operating System | windows 11
| Browser | Google Chrome
Bug details | Steps to reproduce | when trying to login,user should be redirected to the home page after logging in,however page just refreshes as there is no back end data being sent
| Expected result | should be logged in and sent to the home page
| Actual result | page just refreshes back to log in page
Bug tracking | Severity | Major
| Assigned to | lewis
| Priority | High
Notes | Notes | back end bugs need fixing
Category | Label | Value
Bug ID | ID Number | #06
| Title | user unable to register and be sent to home page
| Reporter | damian knight
| Submit date | 2024-12-12
Bug overview | Summary | due to backend link up having bugs with front end no data is being sent through so unable to register
Environment | Platform | vs code
| Operating System | windows 11
| Browser | Google Chrome
Bug details | Steps to reproduce | go to register page,enter details and try to register by clicking register
| Expected result | registered user should be created and redirected to the main home page
| Actual result | page refreshes and stays on register with no effect
Bug tracking | Severity | major
| Assigned to | lewis
| Priority | High
Notes | Notes | back end bugs need fixing
Category | Label | Value
Bug ID | ID Number | #07
| Title | UI components are misaligned.
| Reporter | John Webb
| Submit date | 2024-11-20
Bug overview | Summary | Buttons, text boxes, and dropdowns overlap or misalign on the home page
Environment | Platform | Windows
| Operating System | 11
| Browser | Chrome
Bug details | Steps to reproduce | Click home in Navbar to go to home page
| Expected result | Content box should sit in the centre of the screen
| Actual result | Content box is misaligned and not properly displaying content
Bug tracking | Severity | Major
| Assigned to | John Webb
| Priority | High
Notes | Notes
Category | Label | Value
Bug ID | ID Number | #08
| Title | Unable to navigate to the guest page as the default.
| Reporter | Damian
| Submit date | 2024-06-12
Bug overview | Summary | Users are unable to navigate to the guest page automatically when visiting the site for the first time.
Environment | Platform | Windows
| Operating System | 11
| Browser | Chrome
Bug details | Steps to reproduce | Open localhost:3000
| Expected result | The user should be automatically navigated to the guest page.
| Actual result | User is navigated to home page instead
Bug tracking | Severity | Major
| Assigned to | John Webb
| Priority | High
Notes | Notes
Category | Label | Value
Bug ID | ID Number | #09
| Title | Unable to receive error message with invalid credentials
| Reporter | John Webb
| Submit date | 2024-06-12
Bug overview | Summary | The system is not doing anything when login button is pressed
Environment | Platform | Windows
| Operating System | Windows
| Browser | Chrome
Bug details | Steps to reproduce | Navigate to the login page and enter invalid credentials.
| Expected result | The system should display an error message: "Invalid credentials."
| Actual result | Nothing happens
Bug tracking | Severity | Major
| Assigned to | Lewis
| Priority | High
Notes | Notes
Category | Label | Value
Bug ID | ID Number | #10
| Title | Admin cannot view user data after login
| Reporter | John Webb
| Submit date | 2024-12-12
Bug overview | Summary | The admin is unable to view user data after searching for a specific account.
Environment | Platform | Windows
| Operating System | 11
| Browser | Chrome
Bug details | Steps to reproduce | Log in with valid admin credentials and go to the 'Admin Tab'. Select 'Search Account' and search for a specific account."
| Expected result | Admin should be able to see the details of the searched user account.
| Actual result | There is no data to access from backend so admin cannot view user
Bug tracking | Severity | Major
| Assigned to | Lewis
| Priority | High
Notes | Notes
Category | Label | Value
Bug ID | ID Number | #11
| Title | User can access admin section
| Reporter | John Webb
| Submit date | 2024-12-12
Bug overview | Summary | When a user clicks on the admin tab they are able to access the page
Environment | Platform | Windows
| Operating System | 11
| Browser | Chrome
Bug details | Steps to reproduce | Login as a user and click on the admin page
| Expected result | Unable to acces admin page
| Actual result | Unable to login as a user, or access admin due to lack of backend capabilities
Bug tracking | Severity | Major
| Assigned to | Lewis
| Priority | High
Notes | Notes